## A2. Minor sites full consent
A2. Phasing non-Major applications with full consent
Application number | Policy Site reference | Decision date | Site Address | Parish | Easting | Northing | Status end of 2024/25 | Extant Units 2024/25 | Phasing 2025/26 | Phasing 2026/27 | Phasing 2027/28 | Phasing 2028/29 | Phasing 2029/30 | Five year Total
14/00176 |  | 2014-06-11 | Hope Bay, The Leas, Kingsdown | Ringwould with Kingsdown | 637874 | 146635 | Under Construction | 2 | 2 |  |  |  |  | 2
15/01243 |  | 2016-12-15 | Land at North End, Channel View Road, | Dover | 631450 | 140629 | Under Construction | 1 | 1 |  |  |  |  | 1
17/00070 |  | 2017-05-05 | 93 High Street, | Dover | 631366 | 141934 | Under Construction | 1 | 1 |  |  |  |  | 1
17/00082 |  | 2017-03-24 | 22-24 Castle Street | Dover | 632127 | 141555 | Under Construction | 4 | 4 |  |  |  |  | 4
17/00246 |  | 2018-04-30 | Old Rectory, Church Hill, | Eythorne | 627994 | 149647 | Under Construction | 9 | 4 | 5 |  |  |  | 9
17/00358 |  | 2017-05-23 | Flats 3 & 4 10 Prince of Wales Terrace, Deal | Deal | 637813 | 152367 | Under Construction | -1 | -1 |  |  |  |  | -1
17/01446 |  | 2018-07-19 | Land to the rear of 59 and 61 Maison Dieu Road, | Dover | 631540 | 142111 | Under Construction | 2 | 2 |  |  |  |  | 2
18/00014 |  | 2018-03-13 | 28 Castle Street | Dover | 632114 | 141551 | Under Construction | 2 | 2 |  |  |  |  | 2
18/00450 |  | 2018-07-20 | 209 Folkestone Road, | Dover | 630855 | 141198 | Under Construction | 3 | 3 |  |  |  |  | 3
18/00592 |  | 2019-11-27 | Land R/O Station Road | Walmer | 636628 | 149698 | Under Construction | 0 | 0 |  |  |  |  | 0
18/00796 |  | 2018-10-30 | 113 London Road | Deal | 637024 | 152278 | Under Construction | 1 | 1 |  |  |  |  | 1
18/00977 |  | 2019-10-04 | The Old Pumphouse, Beacon Lane, | Woodnesborough | 630039 | 156618 | Under Construction | 0 | 0 |  |  |  |  | 0
18/01321 |  | 2019-07-17 | The Old Railway Station, Canterbury Road, | Wingham | 623820 | 157280 | Under Construction | 1 | 1 |  |  |  |  | 1
19/00231 |  | 2019-07-05 | 177 Telegraph Road | Deal | 636893 | 151065 | Under Construction | 1 | 1 |  |  |  |  | 1
19/00856 |  | 2020-02-04 | Land rear of 56 Sandwich Road, | Eythorne | 628425 | 149437 | Under Construction | 1 | 1 |  |  |  |  | 1
19/00910 |  | 2019-10-31 | 90 Oswald Road, | Dover | 630693 | 142572 | Under Construction | 1 | 1 |  |  |  |  | 1
19/01028 |  | 2019-11-05 | 61 Mill Lane, Shepherdswell | Shepherdswell with Coldred | 626538 | 148118 | Under Construction | 1 | 1 |  |  |  |  | 1
19/01083 |  | 2019-11-08 | Land rear of Grove House, 14 Wigmore Lane, horne | Eythorne | 628158 | 149648 | Under Construction | 1 | 1 |  |  |  |  | 1
19/01092 |  | 2020-04-20 | Mellands Farm, Stourmouth Road | Preston | 625253 | 161730 | Under Construction | 1 | 1 |  |  |  |  | 1
19/01249 |  | 2020-04-20 | Land R/O 22, The Droveway, St Margarets Bay | St Margaret's at Cliffe | 636499 | 144538 | Under Construction | 1 | 1 |  |  |  |  | 1
19/01337 |  | 2020-11-20 | Beacon Lane Farm, Beacon Lane, | Woodnesborough | 630134 | 156664 | Under Construction | 4 | 4 |  |  |  |  | 4
19/01412 |  | 2020-01-17 | 28 and 30 Mill Road | Deal | 637352 | 152363 | Under Construction | 2 | 2 |  |  |  |  | 2
19/01473 |  | 2020-07-17 | Newlands Farm, Stoneheap Road, East Studdal | Sutton by Dover | 632265 | 150191 | Not Started | 3 | 0 | 3 |  |  |  | 3
19/01525 |  | 2022-09-13 | Lower Rowling Farm, Rowling Road, | Goodnestone | 627822 | 154948 | Under Construction | 8 | 4 | 4 |  |  |  | 8
19/01555 |  | 2020-02-27 | The Quinces, Sheerwater Road, Ash | Ash | 626733 | 160567 | Under Construction | 0 | 0 |  |  |  |  | 0
20/00102 |  | 2020-05-21 | Depot, Masons Road, | Dover | 630506 | 142160 | Under Construction | 2 | 2 |  |  |  |  | 2
20/00541 |  | 2023-01-13 | Land on the West Side of Station Road, | St Margaret's at Cliffe | 635658 | 145020 | Under Construction | 4 | 4 |  |  |  |  | 4
20/00544 |  | 2022-09-27 | Meadow Cottage and Lane Rear of The Street, | Preston | 625049 | 161140 | Not Started | 4 | 0 | 2 | 2 |  |  | 4
20/00566 |  | 2020-11-24 | Delfbridge Manor, 10 Dover Road | Sandwich | 633177 | 157581 | Under Construction | 8 | 4 | 4 |  |  |  | 8
20/00623 |  | 2023-01-26 | Church Farm, The Street | Staple | 626974 | 156584 | Not Started | 5 | 0 | 2 | 3 |  |  | 5
20/00895 |  | 2021-03-31 | 9 Park Place | Dover | 631660 | 141859 | Not Started | 1 | 0 | 1 |  |  |  | 1
20/00908 |  | 2021-04-28 | Lodge Lees Farm, Lodge Lees Road, Denton | Denton with Wootton | 620552 | 147421 | Under Construction | 1 | 1 |  |  |  |  | 1
20/00979 |  | 2021-04-06 | Glen Farm, Mongeham Road, | Ripple | 634724 | 150178 | Not Started | 1 | 0 | 1 |  |  |  | 1
20/00989 |  | 2021-03-05 | Townsend Farm, The Street | Northbourne | 633291 | 152081 | Not Started | 3 | 0 | 3 |  |  |  | 3
20/00996 |  | 2021-09-10 | Vine Farm, Parsonage Farm Road, Marshborough | Woodnesborough | 630572 | 157339 | Under Construction | 1 | 1 |  |  |  |  | 1
20/01063 |  | 2020-12-22 | Morfield House, 11 Bewsbury Crescent | Whitfield | 629822 | 145219 | Under Construction | 1 | 1 |  |  |  |  | 1
20/01171 |  | 2021-02-09 | Land known as Church Farm, Vicarage Farm Road, West Langdon | Langdon | 631963 | 147351 | Under Construction | 1 | 1 |  |  |  |  | 1
20/01245 |  | 2022-09-29 | Site South of Marlborough Road | Deal | 636105 | 150929 | Not Started | 9 | 0 | 4 | 5 |  |  | 9
20/01266 |  | 2021-08-02 | Deacon Landscape Management Wootton Lane Wootton Canterbury Kent | Denton with Wootton | 622270 | 146149 | Not Started | 8 | 0 | 4 | 4 |  |  | 8
20/01311 |  | 2022-12-12 | 101 Sandwich Road | Ash | 629775 | 158359 | Not Started | 1 | 0 | 1 |  |  |  | 1
20/01394 |  | 2021-01-19 | 7 Bewsbury Crescent | Whitfield | 629807 | 145240 | Not Started | 1 | 0 | 1 |  |  |  | 1
20/01409 |  | 2021-01-27 | Hogbrook Farm, Hogbrook Hill Lane | Alkham | 625650 | 142127 | Under Construction | 1 | 1 |  |  |  |  | 1
20/01469 |  | 2022-09-15 | 1 Yew Tree Cottages, Holt Street, | Nonington | 625195 | 151566 | Not Started | 1 | 0 | 1 |  |  |  | 1
20/01482 |  | 2023-03-07 | Land Between 82 and 86 Wellington Parade, | Walmer | 637944 | 148998 | Under Construction | 1 | 1 |  |  |  |  | 1
21/00141 |  | 2022-12-23 | Barn At Staple Farm, Durlock Road | Staple | 627235 | 156866 | Not Started | 4 | 0 | 2 | 2 |  |  | 4
21/00317 |  | 2022-03-22 | Coastguard Cottages Bay Hill St Margarets Bay | St Margaret's at Cliffe | 636465 | 144364 | Under Construction | 5 | 2 | 3 |  |  |  | 5
21/00324 |  | 2021-10-06 | The Barn, Crown Inn, The Street, Finglesham | Northbourne | 633770 | 153797 | Not Started | 2 | 0 | 2 |  |  |  | 2
21/00377 |  | 2022-02-22 | New House Farm Church Lane | Stourmouth | 625630 | 162270 | Not Started | 3 | 0 | 3 |  |  |  | 3
21/00391 |  | 2022-10-07 | Land Adjacent to 95 The Street | Ash | 628958 | 158368 | Not Started | 1 | 0 | 1 |  |  |  | 1
21/00413 |  | 2022-10-07 | Former Grain Barn, Pixwell Lane, | Great Mongeham | 634666 | 151262 | Not Started | 5 | 0 | 2 | 3 |  |  | 5
21/00456 |  | 2021-05-19 | 1 Good Hope, Glack Road | Deal | 635746 | 151791 | Under Construction | 1 | 1 |  |  |  |  | 1
21/00469 |  | 2021-05-17 | 29a Adelaide Road, Elvington | Eythorne | 627750 | 150329 | Under Construction | 2 | 2 |  |  |  |  | 2
21/00506 |  | 2021-07-27 | Hours, Church Road, Coldred, Shepherdswell with Coldred | Shepherdswell with Coldred | 627188 | 147203 | Under Construction | 0 | 0 |  |  |  |  | 0
21/00605 |  | 2021-07-13 | 3 The Chain | Sandwich | 633193 | 158009 | Under Construction | 1 | 1 |  |  |  |  | 1
21/00627 |  | 2022-04-28 | Rear of 12-16 Victoria Road and Fronting Sondes Road | Deal | 637719 | 152451 | Not Started | 6 | 0 | 3 | 3 |  |  | 6
21/00649 |  | 2022-01-07 | Dambridge Farm, Dambridge Oast, Dambridge Farm Road | Wingham | 624969 | 157220 | Under Construction | 2 | 2 |  |  |  |  | 2
21/00766 |  | 2021-10-06 | Richborough Farm, Richborough Road, Richborough | Ash | 631724 | 160600 | Not Started | 4 | 0 | 2 | 2 |  |  | 4
21/00776 |  | 2021-12-10 | Land fronting St Marys Road, rear of Redcote, St Clare Road | Walmer | 637235 | 150201 | Under Construction | 2 | 2 |  |  |  |  | 2
21/00805 |  | 2021-10-19 | Victoria House, 101 Sandwich Road | Whitfield | 630114 | 145495 | Not Started | 4 | 0 | 2 | 2 |  |  | 4
21/00821 |  | 2021-07-13 | 10 Priory Street, | Dover | 631713 | 141574 | Not Started | 1 | 0 | 1 |  |  |  | 1
21/01132 |  | 2021-09-30 | Community Church Deal, Stanley Road | Deal | 637717 | 152397 | Under Construction | 2 | 2 |  |  |  |  | 2
21/01145 |  | 2022-02-11 | Ivy Bank 33 Granville Road St Margarets Bay | St Margaret's at Cliffe | 636861 | 144688 | Under Construction | 0 | 0 |  |  |  |  | 0
21/01175 |  | 2022-01-13 | 67-69 High Street | Dover | 631406 | 141890 | Under Construction | 6 | 3 | 3 |  |  |  | 6
21/01183 |  | 2021-09-30 | Halstead, Gore Lane, | Eastry | 630694 | 155245 | Under Construction | 0 | 0 |  |  |  |  | 0
21/01201 |  | 2021-12-16 | 10 Cattle Market, | Sandwich | 632941 | 158182 | Under Construction | 2 | 2 |  |  |  |  | 2
21/01237 |  | 2024-07-10 | Phase 2, Land south of Mill Field | Ash | 629349 | 158171 | Under Construction | 9 | 4 | 5 |  |  |  | 9
21/01272 |  | 2021-11-02 | Agricultural Building south east of Elmstone Court Farm, Padbrook Lane, Elmstone | Preston | 625789 | 159924 | Not Started | 1 | 0 | 1 |  |  |  | 1
21/01309 |  | 2022-04-06 | Rose Nursery, Dover Road, | Sandwich | 632376 | 156714 | Not Started | 7 | 0 | 3 | 4 |  |  | 7
21/01360 |  | 2021-11-24 | Site at Chapel Lane, Chapel Lane, Ashley | Sutton by Dover | 630897 | 148639 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01375 |  | 2022-09-16 | 33 High Street, | Dover | 631472 | 141829 | Not Started | 3 | 0 | 3 |  |  |  | 3
21/01386 |  | 2022-06-01 | Highleas Old Court Hill, | Aylesham | 624863 | 152842 | Under Construction | 3 | 3 |  |  |  |  | 3
21/01394 |  | 2021-10-20 | Generals Meadow Nursing Home, St Clare Road | Walmer | 637185 | 150091 | Under Construction | 0 | 0 |  |  |  |  | 0
21/01402 |  | 2022-05-05 | The Edge Bay, Hill Street, St Margaret's Bay | St Margaret's at Cliffe | 636794 | 144504 | Not Started | 0 | 0 |  |  |  |  | 0
21/01444 |  | 2022-04-26 | Shop to Rear of 11 Prince of Wales Terrace | Deal | 637800 | 152348 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01558 |  | 2022-06-13 | 26 Coombe Valley Road, | Dover | 630805 | 142383 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01581 |  | 2023-02-28 | Felder Lodge, Deal Road, Worth | Worth | 632983 | 155938 | Under Construction | 2 | 2 |  |  |  |  | 2
21/01587 |  | 2022-11-24 | Oast House, Preston Road | Stourmouth | 625506 | 162013 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01601 |  | 2022-07-22 | Garage The Old Coach House, Sondres Road | Deal | 637728 | 152470 | Not Started | 1 | 0 | 1 |  |  |  | 1
21/01606 |  | 2024-03-05 | Whiteville, Lawn Road | Walmer | 637220 | 150447 | Not Started | 2 | 0 | 2 |  |  |  | 2
21/01641 |  | 2022-01-19 | 73 Hillside Road | Dover | 630319 | 142707 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01682 |  | 2022-09-14 | 17 South Avenue, Snowdown | Aylesham | 624396 | 151150 | Not Started | 1 | 0 | 1 |  |  |  | 1
21/01710 |  | 2022-11-18 | Land West of 455 Folkestone Road, | Dover | 629946 | 140498 | Not Started | 5 | 0 | 2 | 3 |  |  | 5
21/01714 |  | 2022-09-16 | The Rookery, Durlock Road | Staple | 627456 | 157090 | Not Started | 0 | 0 |  |  |  |  | 0
21/01760 |  | 2022-09-16 | 17 Church Street | Walmer | 636820 | 150292 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01762 |  | 2022-03-02 | Land At Eythorne Court Cottage Shepherdswell Road | Eythorne | 628030 | 149568 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01777 |  | 2022-05-19 | 140 Crabble Hill | Dover | 630140 | 143116 | Not Started | 2 | 0 | 2 |  |  |  | 2
21/01783 |  | 2022-09-22 | Land Adjoining 4 Woodnesborough Road, | Sandwich | 632702 | 158007 | Not Started | 2 | 0 | 2 |  |  |  | 2
21/01827 |  | 2022-11-29 | 5 Mill Bank, Mill Lane, | Eastry | 630254 | 154556 | Under Construction | 2 | 2 |  |  |  |  | 2
21/01900 |  | 2022-12-21 | 2 Canute Road | Deal | 637410 | 154099 | Under Construction | 1 | 1 |  |  |  |  | 1
21/01906 |  | 2022-03-23 | Ground Floor 109 High Street | Dover | 631338 | 141960 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00074 |  | 2022-03-25 | 7-9 Chilton Way | River | 629031 | 143430 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00077 |  | 2022-10-20 | Land South of Downs Cottage, Grove Road, | Preston | 624773 | 161119 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00084 |  | 2022-04-01 | St Richards Road Surgery 227 St Richards Road | Deal | 635794 | 151243 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00121 |  | 2022-04-28 | Land Rear of 59 to 61 Maison Dieu Road | Dover | 631527 | 142093 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/00141 |  | 2022-07-29 | Land South of The Oast, Preston Lane | Preston | 624811 | 160038 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00143 |  | 2024-10-15 | Land adjoining Cilcain Winehouse Lane | Capel-le-Ferne | 625741 | 138588 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00166 |  | 2022-05-12 | The Old Pumphouse, Beacon Lane, | Woodnesborough | 630038 | 156625 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00170 |  | 2022-10-17 | Land South West of Tryster, Ellens Road | Deal | 635614 | 150985 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00182 |  | 2022-07-13 | 19 De Burgh Street, | Dover | 631300 | 141921 | Under Construction | 0 | 0 |  |  |  |  | 0
22/00333 |  | 2022-11-22 | Land South East Of Birnam Mushroom Farm, Hammill Road, Woodnesborough | Woodnesborough | 629884 | 156366 | Under Construction | 2 | 2 |  |  |  |  | 2
22/00335 |  | 2023-05-10 | 127 Capel Street | Capel-le-Ferne | 625009 | 139297 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00386 |  | 2022-06-09 | 19 Castle Street | Dover | 632115 | 141585 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00405 |  | 2022-05-25 | Rhylyn Downs Road, East Studdal | Sutton by Dover | 632679 | 149715 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00433 |  | 2022-05-12 | Clampits Cottage, the Clampits Farm, Wass Dove, Westmarsh | Ash | 627954 | 161136 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/00450 |  | 2022-07-12 | Agricultural Farm and Buildings, Minnis Farm, Minnis Way | Worth | 633885 | 156166 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00471 |  | 2024-02-23 | 3 Middle Deal Road | Deal | 637262 | 152684 | Not Started | 4 | 0 | 2 | 2 |  |  | 4
22/00472 |  | 2023-07-14 | The Stables, Great Knell Farm, Knell Lane | Ash | 628471 | 160193 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00488 |  | 2022-09-13 | 30-32 Castle Street | Dover | 632110 | 141548 | Under Construction | 2 | 2 |  |  |  |  | 2
22/00495 |  | 2022-06-24 | Land at 5 Beechwood Close | Whitfield | 630097 | 146070 | Under Construction | 1 | 0 | 1 |  |  |  | 1
22/00676 |  | 2022-08-25 | 86 and Part 84 Leburne Road, | Dover | 632068 | 141899 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/00724 |  | 2023-02-17 | Railway Crossing Cottage, Ash Road, | Sandwich | 632388 | 158536 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00746 |  | 2023-08-08 | Land Rear Of 162-164 & Part Of 162 Mongeham Road | Great Mongeham | 635168 | 151685 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00768 |  | 2023-09-14 | 215 St Richards Road | Deal | 635944 | 151212 | Under Construction | 8 | 4 | 4 |  |  |  | 8
22/00832 |  | 2023-04-20 | Capel Court Park, New Dover Road | Capel-le-Ferne | 625551 | 138704 | Under Construction | 5 | 2 | 3 |  |  |  | 5
22/00847 |  | 2022-10-17 | 42 King Street, | Sandwich | 633132 | 158050 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00896 |  | 2022-10-20 | Land Opposite Paddledock Manor Church Lane | Stourmouth | 625404 | 162571 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00904 |  | 2022-10-26 | 16 Park Avenue | Dover | 631698 | 142193 | Not Started | 0 | 0 |  |  |  |  | 0
22/00916 |  | 2023-03-02 | 64-66 Southwall Road | Deal | 636999 | 152662 | Not Started | 7 | 0 | 3 | 4 |  |  | 7
22/00917 |  | 2022-10-04 | 66 Noahs Ark Road | Dover | 630527 | 141932 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/00979 |  | 2022-10-05 | 215 St Richards Road | Deal | 635944 | 151212 | Under Construction | 1 | 1 |  |  |  |  | 1
22/00980 |  | 2022-12-01 | Preston Garden Centre, The Street | Preston | 625114 | 161161 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01011 |  | 2024-01-23 | Sherleys Far, Reach Road | St Margaret's at Cliffe | 634674 | 143408 | Under Construction | 0 | 0 |  |  |  |  | 0
22/01140 |  | 2022-10-25 | Deaconland Farm, Church Hill, Elmstone | Preston | 626387 | 159884 | Under Construction | 2 | 2 |  |  |  |  | 2
22/01181 |  | 2022-11-02 | Living Well Church, Canterbury Road | Lydden | 627099 | 145398 | Under Construction | 2 | 2 |  |  |  |  | 2
22/01222 |  | 2023-08-04 | Townsend Farm The Street | Northbourne | 633291 | 152080 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01225 |  | 2023-06-27 | Land Adjacent to Fitzwalters Meadow, Boyes Lane | Goodnestone | 625680 | 154916 | Not Started | 3 | 0 | 3 |  |  |  | 3
22/01243 |  | 2023-01-12 | 44-46 Mill Hill | Deal | 636555 | 151403 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/01275 |  | 2022-11-25 | Garage Block in the Centre of Cavell Square | Deal | 636105 | 151501 | Under Construction | 3 | 3 |  |  |  |  | 3
22/01284 |  | 2022-11-25 | 23 High Street | Deal | 637679 | 152598 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01289 |  | 2023-03-27 | 1 & 2 St Margaret's Road, St Margaret's Bay, | St Margaret's at Cliffe | 636342 | 144476 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01297 |  | 2022-11-29 | 9 Beechwood close | Whitfield | 630069 | 146027 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01313 |  | 2023-05-17 | Hull Cottage, Sandwich Road | Sholden | 635153 | 152853 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01315 |  | 2023-06-23 | 54 Albert Road | Deal | 637298 | 152735 | Not Started | 0 | 0 |  |  |  |  | 0
22/01342 |  | 2023-03-28 | The Cabin, Knell Lane | Ash | 628464 | 159295 | Not Started | 0 | 0 |  |  |  |  | 0
22/01368 |  | 2022-12-13 | Third & Fourth Floors, 1 Cannon Street, | Dover | 631912 | 141494 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/01402 |  | 2023-08-17 | 98 New Street | Ash | 629654 | 158081 | Under Construction | 1 | 1 |  |  |  |  | 1
22/01454 |  | 2022-12-23 | Crockshard Farm Oak Barn, Crockshard Hill, | Wingham | 624986 | 155957 | Under Construction | 1 | 1 |  |  |  |  | 1
22/01511 |  | 2023-04-05 | Wellington Fields, Lowslip Hill, West Hougham | Hougham | 627404 | 140435 | Not Started | 0 | 0 |  |  |  |  | 0
22/01513 |  | 2023-01-27 | 9 Macdonald Road, | Dover | 630336 | 142154 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/01553 |  | 2023-01-25 | Sandwich House, The Citadel, Western Heights, | Dover | 630854 | 140448 | Under Construction | 0 | 0 |  |  |  |  | 0
22/01577 |  | 2023-10-16 | Horse Shoe Bungalow, Mill Lane | Preston | 625114 | 160937 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01584 |  | 2023-05-17 | 1 Potter Street | Sandwich | 633051 | 158259 | Under Construction | 2 | 2 |  |  |  |  | 2
22/01601 |  | 2023-06-08 | 233 Folkestone Road | Dover | 630784 | 141166 | Under Construction | -1 | -1 |  |  |  |  | -1
22/01611 |  | 2023-02-13 | 47-49 Queen Street | Deal | 637523 | 152540 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/01616 |  | 2023-05-06 | Cooks Place, Preston Road | Stourmouth | 625715 | 162125 | Not Started | 0 | 0 |  |  |  |  | 0
22/01620 |  | 2023-02-02 | 6A Minnis Terrace, Crabble Avenue, | Dover | 630255 | 142768 | Not Started | 0 | 0 |  |  |  |  | 0
22/01642 |  | 2023-06-08 | Plot 1, Land Adjacent to 22 The Street, West Hougham | Hougham | 626678 | 140205 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/01643 |  | 2023-10-13 | Land to the West of 22 The Street, West Hougham | Hougham | 626657 | 140192 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01666 |  | 2023-07-18 | Ashen Tree House, Ashen Tree Lane | Dover | 632180 | 141647 | Under Construction | 3 | 3 |  |  |  |  | 3
22/01677 |  | 2023-06-22 | Martindale, The Street | Preston | 625046 | 160889 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01679 |  | 2023-02-10 | North Court Plantation Dover Road | Tilmanstone | 630534 | 152035 | Not Started | 2 | 0 | 2 |  |  |  | 2
22/01700 |  | 2023-05-10 | The Frog and Orange, Roman Road, Shatterling | Staple | 626721 | 158324 | Not Started | 1 | 0 | 1 |  |  |  | 1
22/01707 |  | 2023-04-19 | Land between Minnis Terrace and 110 Hillside Road | Dover | 630289 | 142763 | Under Construction | 3 | 3 |  |  |  |  | 3
22/01721 |  | 2023-03-17 | 194 High Street | Deal | 637654 | 153207 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00039 |  | 2024-04-23 | Garages to Centre of Cavell Square | Deal | 636117 | 151508 | Under Construction | 4 | 4 |  |  |  |  | 4
23/00046 |  | 2023-03-10 | Wayfarers St Barts Road. | Sandwich | 632974 | 157535 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00074 |  | 2023-03-16 | The Grain Store, North Court Farmyard, North Court Lane | Tilmanstone | 630263 | 152000 | Not Started | 3 | 0 | 3 |  |  |  | 3
23/00076 |  | 2023-08-31 | Car Park, Military Road | Dover | 631629 | 141472 | Not Started | 8 | 0 | 4 | 4 |  |  | 8
23/00087 |  | 2023-03-07 | 175 St Radigunds Road, | Dover | 630188 | 140020 | Not Started | 0 | 0 |  |  |  |  | 0
23/00109 |  | 2023-03-23 | 34 Cauldham Close | Capel-le-Ferne | 624521 | 138408 | Not Started | 3 | 0 | 3 |  |  |  | 3
23/00119 |  | 2023-08-01 | 8 The Street | Ash | 628409 | 158426 | Not Started | 6 | 3 | 3 |  |  |  | 6
23/00129 |  | 2023-05-12 | Upton Court Farm, Coldred Road, | Shepherdswell with Coldred | 626271 | 147733 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00147 |  | 2024-02-08 | Hughenden House, Maison Dieu Vetinary Centre, 7 Sondres Road | Deal | 637799 | 152467 | Under Construction | 2 | 2 |  |  |  |  | 2
23/00171 |  | 2023-05-10 | Selson Farm, Selson Lane | Eastry | 630257 | 155520 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00175 |  | 2023-05-16 | Statenborough Farm Cottage, Felderland Lane, Worth | Eastry | 631803 | 155667 | Not Started | 5 | 0 | 2 | 3 |  |  | 5
23/00203 |  | 2023-12-18 | Store Little, Crockshard Farm, Crockshard Lane | Wingham | 624585 | 155944 | Under Construction | 1 | 1 |  |  |  |  | 1
23/00204 |  | 2023-04-26 | Lealands, 63 The Drove Way, St Margaret's Bay | St Margaret's at Cliffe | 636780 | 144938 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00240 |  | 2024-11-15 | Mansion Gardens, Port Zone, Off Willingdon Road | Whitfield | 630140 | 143965 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00264 |  | 2024-10-16 | Land To The Rear Of Ashurst 162 Mongeham Road | Great Mongeham | 635168 | 151685 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00271 |  | 2024-01-10 | Agricultural Farm and Buildings, Westcourt Farm Westcourt Lane | Shepherdswell with Coldred | 624694 | 148095 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00345 |  | 2023-05-02 | Former Garage, Bock adjacent to No.65 St Davids Avenue, Old Folkestone Road | Dover | 630565 | 140073 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00346 |  | 2023-05-02 | Garage Block next to 40 Old Folkestone Road | Dover | 630574 | 140038 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00352 |  | 2023-05-03 | 59 Crabble Hill | Dover | 630404 | 142995 | Not Started | 0 | 0 |  |  |  |  | 0
23/00356 |  | 2023-05-12 | 15 Worthington Street | Dover | 631763 | 141542 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00417 |  | 2023-06-09 | 7 Cross Road | Deal | 636229 | 150881 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00429 |  | 2023-12-12 | 20 Chestnut Drive, Worth | Worth | 633247 | 155974 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00440 |  | 2023-05-23 | 1 Greengates, Beauxfield | Whitfield | 630325 | 145581 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00460 |  | 2024-01-23 | 35 High Street | Dover | 631466 | 141829 | Not Started | 4 | 0 | 2 | 2 |  |  | 4
23/00473 |  | 2023-12-15 | Jossenblock Farm, The Street, East Langdon | Langdon | 633379 | 146144 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00521 | SAP55 | 2024-08-30 | The Larch, Nursery Beacon Lane | Woodnesborough | 630109 | 156790 | Not Started | 8 | 0 | 4 | 4 |  |  | 8
23/00521 | WOO005 | 2024-08-30 | Beacon Lane Nursery, Beacon Lane, Woodnesborough | Woodnesborough | 630109 | 156790 | Not Started | 8 | 0 | 4 | 4
23/00539 |  | 2023-06-20 | 23A Cannon Street | Dover | 631872 | 141517 | Under Construction | 3 | 3 |  |  |  |  | 3
23/00546 |  | 2024-02-02 | Land East Side of Short Lane | Alkham | 625920 | 142307 | Not Started | 8 | 4 | 4 |  |  |  | 8
23/00563 |  | 2023-08-17 | 29 Monks Way | Dover | 630462 | 143482 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00576 |  | 2023-11-01 | Land South West of Ferrybridge House, Abbey Road | Dover | 629553 | 142196 | Not Started | 2 | 0 | 2 |  |  |  | 2
23/00592 |  | 2024-05-22 | White Post Farmhouse, 24 Sandwich Road | Ash | 629178 | 158428 | Under Construction | 3 | 3 |  |  |  |  | 3
23/00594 |  | 2023-11-30 | 1 Mayfield Villas, Station Road | Shepherdswell with Coldred | 625824 | 148234 | Under Construction | 1 | 1 |  |  |  |  | 1
23/00623 |  | 2023-07-06 | Land to the Rear of 7 Bewsbury Crescent | Whitfield | 629807 | 145240 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00629 |  | 2023-07-07 | 44 Eythorne Road | Shepherdswell with Coldred | 626105 | 148386 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00630 |  | 2024-03-07 | The Chequers, Golf Road | Sholden | 636819 | 155665 | Not Started | 1 | 1 |  |  |  |  | 1
23/00647 |  | 2024-07-02 | Mellands Farm, Stourmouth Road | Preston | 625253 | 161730 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00667 |  | 2023-07-21 | 12 Tower Hamlets Road | Dover | 631316 | 141955 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00770 |  | 2023-12-15 | 15 The Grange | Shepherdswell with Coldred | 625730 | 148087 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00771 |  | 2024-03-20 | 25 Ravenscourt Road | Walmer | 637460 | 152045 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00782 |  | 2025-02-20 | Huis Close 124 Wellington Parade, Kingsdown | Ringwould with Kingsdown | 637991 | 148680 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00791 |  | 2023-08-09 | Romney House The Citadel Citadel Road | Dover | 630778 | 140500 | Under Construction | 1 | 1 |  |  |  |  | 1
23/00792 |  | 2023-08-09 | Hastings House The Citadel Western Heights | Dover | 630875 | 140506 | Under Construction | 1 | 1 |  |  |  |  | 1
23/00845 |  | 2023-10-11 | 97 High Street | Wingham | 624384 | 157858 | Under Construction | 1 | 1 |  |  |  |  | 1
23/00879 |  | 2023-09-28 | 20 Biggin Street | Dover | 631786 | 141636 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00880 |  | 2023-08-29 | Land adjacent to 16 Granville Road, St Margaret's Bay | St Margaret's at Cliffe | 636560 | 144524 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/00892 |  | 2023-10-13 | The Coach House, High Street | Wingham | 624391 | 157516 | Under Construction | 1 | 1 |  |  |  |  | 1
23/00918 |  | 2024-05-10 | 2A Canada Road | Walmer | 637659 | 151445 | Not Started | 1 | 1 |  |  |  |  | 1
23/00995 |  | 2024-03-05 | Land to the rear of 439 Folkestone Road | Dover | 630082 | 140554 | Under Construction | 2 | 2 |  |  |  |  | 2
23/01009 |  | 2023-11-29 | 35 High Street | Deal | 637688 | 152635 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01043 |  | 2023-11-09 | 119 Sandwich Road, Whitfield | Whitfield | 630139 | 145831 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01044 |  | 2023-12-20 | Rear of 89-91 Folkestone Road | Dover | 631334 | 141366 | Not Started | 2 | 0 | 2 |  |  |  | 2
23/01056 |  | 2024-01-26 | Minnis Farm, Downs Road | Worth | 633884 | 156166 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01070 |  | 2023-11-13 | Hay and Cattle Barn, North Court Farmyard, North Court Lane | Tilmanstone |  |  | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01097 |  | 2024-08-21 | Land South West of Yamaga, The Avenue | Temple Ewell | 628987 | 144339 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01128 |  | 2024-03-20 | Saracens Head, 1 Alfred Square | Deal | 637641 | 153281 | Under Construction | 1 | 1 |  |  |  |  | 1
23/01145 |  | 2024-04-23 | 20 Mongeham Road | Deal | 635723 | 152080 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01147 |  | 2023-12-20 | 96 Sandwich Road | Eythorne | 628525 | 149701 | Not Started | 2 | 0 | 2 |  |  |  | 2
23/01148 |  | 2023-12-20 | 96 Sandwich Road | Eythorne | 628525 | 149701 | Not Started | 0 | 0 |  |  |  |  | 0
23/01192 |  | 2023-12-11 | Buckland Mill, Crabble Hill | Dover | 630550 | 142776 | Under Construction | 2 | 2 |  |  |  |  | 2
23/01231 |  | 2024-05-17 | 8 Green Lane | Eythorne | 628552 | 149429 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01234 |  | 2024-06-18 | 51 Church Path | Deal | 637113 | 152648 | Not Started | 1 | 1 |  |  |  |  | 1
23/01236 |  | 2024-10-21 | Land at The Street, East Langdon | Langdon | 633645 | 146360 | Not Started | 9 | 0 | 4 | 5 |  |  | 9
23/01239 |  | 2024-02-26 | Greenleaves, Caravan, Preston Road | Stourmouth | 626209 | 162156 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01242 |  | 2024-07-16 | Glen Farm, Mongeham Road | Ripple | 634724 | 150178 | Not Started | 2 | 0 | 2 |  |  |  | 2
23/01245 |  | 2024-02-15 | 28 Clarendon Road | Dover | 631339 | 141274 | Not Started | 0 | 0 |  |  |  |  | 0
23/01254 |  | 2024-06-19 | The Cedars 26 Victoria Road | Deal | 637718 | 152384 | Not Started | 1 | 1 |  |  |  |  | 1
23/01255 |  | 2024-07-12 | 377 London Road | Deal | 636020 | 152020 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01265 |  | 2024-02-27 | 7 The Butchery | Sandwich | 633025 | 158281 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01277 |  | 2023-12-15 | Dining Room, The Citadel | Dover | 630777 | 140593 | Under Construction | 0 | 0 |  |  |  |  | 0
23/01282 |  | 2024-04-16 | 26-27 Tower Hamlets Street | Dover | 631030 | 141823 | Under Construction | 1 | 1 |  |  |  |  | 1
23/01294 |  | 2024-01-30 | Cour-Jardin Glebe Close | St Margaret's at Cliffe | 635738 | 144539 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01319 |  | 2024-05-23 | 21 Market Street | Sandwich | 633034 | 158246 | Not Started | 3 | 0 | 3 |  |  |  | 3
23/01324 |  | 2024-11-28 | 20 Granville Road | Walmer | 637561 | 150432 | Under Construction | 1 | 1 |  |  |  |  | 1
23/01328 |  | 2024-02-14 | 4A Bench Street | Dover |  |  | Not Started | 3 | 0 | 3 |  |  |  | 3
23/01336 |  | 2024-10-02 | Neptune Bay Hill, St Margaret's Bay | St Margaret's At Cliffe | 636656 | 144482 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01353 |  | 2024-06-26 | Land West of Nandeos, Saunders Lane | Ash | 629758 | 158040 | Under Construction | 1 | 1 |  |  |  |  | 1
23/01379 |  | 2024-01-31 | 4 Bewsbury Cross Lane | Whitfield | 630041 | 145029 | Not Started | 1 | 0 | 1 |  |  |  | 1
23/01389 |  | 2024-08-05 | Statenborough Farm, Felderlane Lane | Worth | 631803 | 155667 | Not Started | 2 | 0 | 2 |  |  |  | 2
23/01400 |  | 2024-10-10 | Frampton, Hougham Court Lane, Church Hougham | Hougham | 627521 | 139263 | Not Started | 0 | 0 |  |  |  |  | 0
23/01454 |  | 2024-09-23 | Marleybrook House Stourmouth Road | Preston | 624864 | 161801 | Not Started | 0 | 0 |  |  |  |  | 0
24/00001 |  | 2024-02-20 | 21 Castle Street | Dover | 632111 | 141581 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00054 |  | 2024-08-07 | Land rear of Sideways Downs Road, East Studdall | Sutton by Dover | 632231 | 149772 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00068 |  | 2024-06-19 | 6 St Peter's Street | Sandwich | 633132 | 158083 | Not Started | 0 | 1 |  |  |  |  | 1
24/00112 |  | 2024-10-11 | Woodlands, The Avenue, Kingsdown | Ringwould with Kingsdown |  |  | Not Started | -1 | 0 | -1 |  |  |  | -1
24/00117 |  | 2024-05-10 | Malbec, 69 Granville Road | St Margaret's At Cliffe | 637087 | 144928 | Under Construction | 0 | 0 |  |  |  |  | 0
24/00119 |  | 2024-06-25 | Preston Garden Centre, The Street | Preston | 625114 | 161161 | Not Started | 5 | 0 | 2 | 3 |  |  | 5
24/00123 |  | 2024-05-21 | Danehurst, Kingsdown Hill, Kingsdown | Ringwould with Kingsdown | 637530 | 147904 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00129 |  | 2024-04-23 | 15 Norman Street | Dover | 631596 | 141622 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00232 |  | 2024-10-11 | Dairy Building, Westcourt Lane | Shepherdswell with Coldred | 624694 | 148095 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00327 |  | 2025-03-17 | 20 Castle Street | Dover | 632134 | 141569 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00353 |  | 2024-07-11 | The Forge, Goodnestone Road, Chillenden | Goodnestone | 626862 | 153701 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00356 |  | 2025-03-20 | Barns At Guilton Farm Guilton | Ash | 627982 | 158217 | Not Started | 5 | 0 | 2 | 3 |  |  | 5
24/00427 |  | 2024-06-13 | 8 London Road | Dover | 631317 | 142043 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00493 |  | 2024-06-18 | 17-23 Queen Street | Deal | 637610 | 152573 | Not Started | 4 | 0 | 2 | 2 |  |  | 4
24/00551 |  | 2024-08-16 | 76-77 Maison Dieu Road | Dover | 631716 | 141966 | Under Construction | 4 | 4 |  |  |  |  | 4
24/00567 |  | 2024-10-28 | 122 London Road | Dover | 630813 | 142558 | Not Started | 0 | 0 |  |  |  |  | 0
24/00586 |  | 2024-07-19 | 142A High Street | Deal | 637671 | 153021 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00588 |  | 2024-10-25 | Little Westhill Farm, Belsey Lane, Ewell Minnis | Alkham | 625943 | 143363 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00605 |  | 2025-02-25 | Drellingore Barns, Stombers Lane, Drellingore | Alkham | 624073 | 141114 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00649 |  | 2024-10-21 | 196-197 London Road | Dover | 630728 | 142600 | Not Started | 2 | 0 | 2 |  |  |  | 2
24/00652 |  | 2024-10-11 | 62 Canterbury Road | Lydden | 627018 | 145418 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00674 |  | 2024-08-14 | 74 The Street | Ash | 628866 | 158406 | Under Construction | 1 | 1 |  |  |  |  | 1
24/00758 |  | 2025-03-14 | The Bungalow Willow Woods Road Little Mongeham | Great Mongeham | 633373 | 150880 | Not Started | 0 | 0 |  |  |  |  | 0
24/00790 |  | 2024-10-25 | Community Church Deal, Stanley Road | Deal | 637712 | 152425 | Not Started | 2 | 0 | 2 |  |  |  | 2
24/00813 |  | 2024-09-27 | Barnsole Vineyard Fleming Road Staple | Staple | 628084 | 156740 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00818 |  | 2025-02-07 | Electric House 43 Castle Street | Dover |  |  | Not Started | 0 | 0 |  |  |  |  | 0
24/00884 |  | 2024-10-22 | The Grain Store, North Court Farmyard, North Court Lane | Tilmanstone | 630263 | 152000 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/00945 |  | 2025-02-19 | Hillside Pommeus Lane | Sutton by Dover | 634560 | 149549 | Not Started | 0 | 0 |  |  |  |  | 0
24/00951 |  | 2024-11-20 | 148 Snargate Street | Dover | 631800 | 141083 | Not Started | -1 | 0 | -1 |  |  |  | -1
24/00953 |  | 2024-11-12 | 82 Dover Road | Sandwich | 632876 | 157169 | Not Started | 2 | 0 | 2 |  |  |  | 2
24/00985 |  | 2024-11-18 | Noyna, High Street, | Eastry | 630977 | 154827 | Under Construction | -1 | -1 |  |  |  |  | -1
24/00988 |  | 2025-01-31 | The Hollies Lower Road | Staple | 627582 | 156750 | Not Started | -1 | 0 | -1 |  |  |  | -1
24/01008 |  | 2024-11-19 | Wingleton Farm, Wingleton Lane | Sutton by Dover | 634135 | 149326 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/01043 |  | 2024-11-28 | 71 High Street | Deal | 637683 | 152765 | Not Started | 3 | 0 | 3 |  |  |  | 3
24/01160 |  | 2024-12-23 | Agricultural Building South East Of Beacon Hill House Beacon Lane | Woodnesborough | 630393 | 156986 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/01162 |  | 2025-01-02 | Westbury House 1 Westbury Road | Dover | 630942 | 141016 | Not Started | 1 | 0 | 1 |  |  |  | 1
24/01196 |  | 2025-02-13 | 4 St Johns Road | Dover | 631295 | 141412 | Under Construction | 2 | 2 |  |  |  |  | 2
24/01279 |  | 2025-03-19 | Sentosa Chapel Lane | Ripple | 634941 | 149807 | Not Started | 0 | 0 |  |  |  |  | 0
24/01318 |  | 2025-02-12 | New Barn Farm Preston Road | Stourmouth | 626141 | 162245 | Not Started | 7 | 0 | 3 | 4 |  |  | 7
24/01320 |  | 2025-02-12 | Storage Area Above 4-6 Biggin Street | Dover | 631668 | 141689 | Not Started | 2 | 0 | 2 |  |  |  | 2
[7 empty] | Total | 497 | 167 | 258 | 73 | 0 | 0 | 490

## A3. Major sites full consent
A3. Phasing major applications with full consent
Application number | Policy Site reference | Decision date | Site Address | Parish | Easting | Northing | Status end of 2024/25 | Extant Units 2024/25 | Phasing 2025/26 | Phasing 2026/27 | Phasing 2027/28 | Phasing 2028/29 | Phasing 2029/30 | Five year Total | Phased outside of 5 years | Summary of Phasing 2025
21/00224 |  | 2021-11-25 | Land south east of Fernfield Farm, Fernfield Lane, Hawkinge | Alkham | 622215 | 140764 | Under Construction | 7 | 7 | 0 | 0 | 0 | 0 | 7 | 0 | Site is under construction
23/00951 |  | 2025-02-14 | Phase 3 Parcel 1 Land For Aylesham Village Expansion North of Dorman Avenue | Aylesham | 623947 | 153049 | Not Started | 39 | 20 | 19 | 0 | 0 | 0 | 39 | 0 | Site has full consent, and delivery expected within 5 year period.
20/00693 |  | 2023-02-20 | Aylesham Sports Club, Burgess Road | Aylesham | 624062 | 152703 | Not Started | 21 | 0 | 10 | 11 | 0 | 0 | 21 | 0 | Site has full consent, and delivery expected within 5 year period.
20/01004 |  | 2022-10-03 | Phase 2B Parcel 3 Land for Aylesham Village Expansion, North of Dorman Avenue | Aylesham | 623702 | 152945 | Under Construction | 22 | 22 | 0 | 0 | 0 | 0 | 22 | 0 | Site is under construction
21/00758 |  | 2022-10-20 | Phase 2B Parcel 4 (And residential access road 2B.2 & 2B.3) Land for Aylesham Village Explansion, North of Dorman Avenue | Aylesham | 624009 | 152564 | Under Construction | 19 | 10 | 9 | 0 | 0 | 0 | 19 | 0 | Site is under construction
20/00879 |  | 2022-10-05 | Phase 2B Parcels 5 & 6 Land for Aylesham Village Expansion of North of Dorman Avenue | Aylesham | 623939 | 152387 | Under Construction | 16 | 16 | 0 | 0 | 0 | 0 | 16 | 0 | Site is under construction
22/00043 |  | 2023-06-08 | Land between nos 107 and 127 Capel Street | Capel-le-Ferne | 624929 | 139251 | Not Started | 34 | 0 | 0 | 14 | 20 | 0 | 34 | 0 | Developer response received in 2025. Site has full consent, and delivery expected within 5 year period.
24/00797 / 23/00401 |  | 2024-12-23 | Land Opposite 32 To 38 Cauldham Lane | Capel-le-Ferne | 624517 | 138570 | Not Started | 16 | 5 | 11 | 0 | 0 | 0 | 16 | 0 | Developer response received in 2025, stating completions expected to commemce in 2025/26
20/01569 |  | 2024-02-28 | Longships, Cauldham Lane | Capel-le-Ferne | 624597 | 138535 | Not Started | 14 | 0 | 9 | 5 | 0 | 0 | 14 | 0 | Site has full consent, and delivery expected within 5 year period.
21/01683 |  | 2022-12-21 | Site at Cross Road | Deal | 636217 | 150414 | Under Construction | 76 | 31 | 29 | 16 | 0 | 0 | 76 | 0 | Site is under construction. Developer response received in 2025, phased to reflect this.
21/00896 |  | 2022-03-04 | Land On The North East Side of Middle Deal Road | Deal | 637233 | 152877 | Under Construction | 63 | 30 | 33 | 0 | 0 | 0 | 63 | 0 | Site is under construction. Developer response received in 2025, phased to reflect this.
22/01345 |  | 2024-03-18 | 12 King Street | Deal | 637730 | 152766 | Not Started | 18 | 0 | 9 | 9 | 0 | 0 | 18 | 0 | Site has full consent, and delivery expected within 5 year period.
24/01050 |  | 2025-02-05 | Land South West of Sholden Drive Sandwich Road | Deal | 635479 | 152296 | Not Started | 81 | 0 | 30 | 30 | 21 | 0 | 81 | 0 | Site has full consent, and delivery expected within 5 year period.
24/01117 |  | 2024-12-04 | Grove Villa, 28 Mill Road | Deal | 637352 | 152363 | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Site has full consent, and delivery expected within 5 year period.
18/00892 |  | 2021-11-15 | Land on the West side of Albert Road | Deal | 637270 | 152826 | Under Construction | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | Site is under construction
20/01258 |  | 2022-04-06 | Land West of St Radigunds Community Centre Poulton Close | Dover | 629905 | 141982 | Not Started | 24 | 0 | 0 | 0 | 24 | 0 | 24 | 0 | Site has full consent, and delivery expected within 5 year period.
18/01322 |  | 2019-07-09 | Former Magistrates Court 1 - 7 Pencester Road | Dover | 631956 | 141736 | Not Started | 46 | 0 | 0 | 20 | 26 | 0 | 46 | 0 | Site has full consent, and delivery expected within 5 year period.
20/00510 |  | 2022-05-03 | Karma Leisure Ltd, Adrian Street | Dover | 631907 | 141236 | Not Started | 29 | 0 | 20 | 9 | 0 | 0 | 29 | 0 | Site has full consent, and delivery expected within 5 year period.
20/01014 |  | 2022-10-10 | Land to the Rear of Former Magistrates Court, Pencester Road | Dover | 631956 | 141736 | Not Started | 12 | 0 | 0 | 9 | 3 | 0 | 12 | 0 | Site has full consent, and delivery expected within 5 year period.
19/01025 |  | 2024-09-04 | Land adjoining 74, Stanhope Road | Dover | 631434 | 142717 | Not Started | 32 | 0 | 20 | 12 | 0 | 0 | 32 | 0 | Site has full consent, and delivery expected within 5 year period.
22/01305 |  | 2025-01-17 | Land At Barwick Road | Dover | 629803 | 142017 | Not Started | 120 | 0 | 0 | 45 | 45 | 30 | 120 | 0 | Site has full consent, and delivery expected within 5 year period.
18/01263 |  | 2019-10-21 | Former United Reformed Church, High Street | Dover | 631586 | 141722 | Under Construction | 16 | 8 | 8 | 0 | 0 | 0 | 16 | 0 | Site is under construction
19/00287 |  | 2020-10-15 | Former Playground, North Military Road | Dover | 631593 | 141398 | Not Started | 20 | 0 | 9 | 9 | 2 | 0 | 20 | 0 | Site has full consent, and delivery expected within 5 year period.
18/01377 |  | 2020-12-04 | Land adjacent to Allotments, Folkestone Road, | Dover | 630131 | 140708 | Under Construction | 9 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | Site is under construction
20/01084 |  | 2021-06-29 | Former Buckland Hospital, Coombe Valley Road, | Dover | 630315 | 142032 | Under Construction | 33 | 20 | 13 | 0 | 0 | 0 | 33 | 0 | Site is under construction
19/01364 |  | 2020-06-05 | 7-8 Eastbrook Place, St Marys Residential Home, Maison Dieu Road | Dover | 632099 | 141661 | Not Started | 20 | 0 | 9 | 9 | 2 | 0 | 20 | 0 | Site has full consent, and delivery expected within 5 year period.
14/00240 |  | 2018-08-20 | Eastry Hospital, Mill Lane | Eastry | 630690 | 154549 | Under Construction | 77 | 30 | 30 | 17 | 0 | 0 | 77 | 0 | Site is under construction
21/00504 |  | 2021-06-28 | Land at Gore Lane | Eastry | 630469 | 154947 | Not Started | 50 | 0 | 30 | 20 | 0 | 0 | 50 | 0 | Site has full consent, and delivery expected within 5 year period.
18/00764 |  | 2019-11-22 | Stalco Engineering Works and Land rear of and including 126 Mongeham Road | Great Mongeham | 635213 | 151879 | Under Construction | 34 | 34 | 0 | 0 | 0 | 0 | 34 | 0 | Site is under construction
18/00981 |  | 2019-04-18 | Former Connaught Barracks, Dover Road, (Officers Mess) | Guston | 632178 | 142467 | Under Construction | 24 | 9 | 9 | 6 | 0 | 0 | 24 | 0 | Site is under construction
21/01615 |  | 2024-01-04 | The Old Malt House, Easole Street | Nonington | 626285 | 152232 | Under Construction | 26 | 20 | 6 | 0 | 0 | 0 | 26 | 0 | Site is under construction
22/01379 |  | 2023-04-27 | Site at Betteshanger Sustainable Parks, Betteshanger Road, Betteshanger | Northbourne | 633690 | 153107 | Under Construction | 152 | 8 | 50 | 50 | 44 | 0 | 152 | 0 | Site is under construction. Developer response received in 2025, phased to reflect this.
21/01572 |  | 2003-07-10 | Willowbank | Sandwich | 633537 | 158335 | Under Construction | 221 | 0 | 50 | 50 | 50 | 50 | 200 | 21 | Application varies condition 2 of 20/00166. Several discharge of conditions applications submitted / approved in 24/2025. Delivery expected to re-commence in 2026.
23/01078 |  | 2024-02-06 | Land South West of Sholden Drive, Sandwich Road | Sholden | 635379 | 152618 | Under Construction | 35 | 30 | 5 | 0 | 0 | 0 | 35 | 0 | Site is under construction
22/01409 |  | 2024-10-21 | Land South West of Sholden Drive, Sandwich Road | Sholden | 635376 | 152636 | Not Started | 64 | 0 | 30 | 30 | 4 | 0 | 64 | 0 | Site has full consent, and delivery expected within 5 year period.
22/00817 |  | 2023-04-21 | Land at Church Field Farm, The Street (Houisng element) | Sholden | 635980 | 152340 | Not Started | 48 | 0 | 0 | 0 | 48 | 0 | 48 | 0 | Site has full consent, and delivery expected within 5 year period.
22/00817 |  | 2023-04-21 | Land at Church Field Farm, The Street (care home element - HDT Ratio applied) | Sholden | 635980 | 152340 | Not Started | 31 | 0 | 0 | 31 | 0 | 0 | 31 | 0 | 64 bed care home. Calcualtion toward housing supply as set out in Housing Delivery Test Rule Book. calculation =# bedrooms / #adults per household 64/1.9=48 (rounded down to 31 units) Phased outside of 5 year period.
21/00999 |  | 2022-03-30 | East Studdal Nurseries Downs Road East Studdal | Sutton by Dover | 632602 | 149717 | Under Construction | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | Site is under construction
14/00361 |  | 2015-10-02 | Land off, Station Road | Walmer | 636352 | 149906 | Under Construction /stalled | 155 | 0 | 0 | 0 | 30 | 45 | 75 | 80 | Consent for 223 dwellings. 71 units were complete but delivery issues have led to stalling of construction. It has been confirmed that marketing Phase 2 of the development is underway.Therefore phasing moved to year 4/5 and part outside 5 year period for extant units.
22/00737 |  | 2023-09-27 | Land to rear of Archers Court Road | Whitfield | 630438 | 144771 | Not Started | 28 | 0 | 20 | 8 | 0 | 0 | 28 | 0 | Site has full consent, and delivery expected within 5 year period.
23/00976 |  | 2024-07-19 | Footpath Field, Staple Road | Wingham | 624616 | 157167 | Under Construction | 71 | 44 | 27 | 0 | 0 | 0 | 71 | 0 | Site is under construction, Developer response received and phasing as suggested.
18/00079 | SAP10 | 22/11/218 | Site at Buckland Mill, Crabble Hill (care home element - HDT Ratio applied) | Dover | 630500 | 142874 | Under Construction | 42 | 0 | 0 | 42 | 0 | 0 | 42 | 0 | Under Construction. 80 bed care home. Calcualtion toward housing supply as set out in Housing Delivery Test Rule Book. calculation = # bedrooms / #adults per household 80/1.9=31.57 (rounded down to 42 units)
[7 empty] | Total | 1852 | 360 | 495 | 452 | 319 | 125 | 1751 | 101

## A4. Major sites outline consent
A4. Phasing major applications with outline consent only
Application number | Policy Site reference | Decision date | Site Address | Parish | Easting | Northing | Status end of 2024/25 | Extant Units 2024/25 | Phasing 2025/26 | Phasing 2026/27 | Phasing 2027/28 | Phasing 2028/29 | Phasing 2029/30 | Five year Total | Phased outside of 5 years | Phasing Summary 2025
19/01462 |  | 2022-09-12 | Land North of Orchard View, and West of Saunders Lane | Ash | 629716 | 158216 | Not Started | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | No Reserved Matters application received and no phasing information submitted. Not included within 5 year supply.
22/01497 | ANP7a | 2024-05-17 | Land at 52 New Street | Ash | 629438 | 158316 | Not Started | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | No Reserved Matters application received and no phasing information submitted. Not included within 5 year supply.
24/00257 |  | 2025-03-21 | Land South East Of Great Cauldham Farm Cauldham Lane | Capel-le-Ferne | 624726 | 138667 | Not Started | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 89 | Outline granted in March 2025. No Reserved Matters application received. Developer has provided information on expected phasing, indicating deliery within 5 year period, but as no Reserved Matters received, site is not currently included within 5 year supply.
21/01822 |  | 2024-09-12 | Land on the west side of Cross Road | Deal | 636055 | 150532 | Not Started | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | Outline granted in Septermber 2024. Developer Progress on dishcharge of conditions applications in summer 2025. No phasing information provided so not currently included within 5 year supply.
20/01068 |  | 2023-12-08 | Buckland Mill, Crabble Hill | Dover | 630369 | 143007 | Not Started | 135 | 0 | 0 | 0 | 51 | 47 | 98 | 37 | Outline granted in 2023. Developer in discussions with Council in relation to discharge of conditions and in relation to phasing of site. No Reserved Matters received but developer information supplied anticipates first completions in 2027/2028. Phasing moved for part of site to years 4/5.
21/00935 |  | 2022-08-24 | 36A Coombe Valley Road, | Dover | 630566 | 142272 | Not Started | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | No Reserved Matters application received and no phasing information submitted. Not included within 5 year supply.
17/01452 |  | 2023-04-28 | Buckland Mill, Service Station, Crabble Hill | Dover | 630326 | 143040 | Not Started | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | No Reserved Matters application received and no phasing information submitted. Not included within 5 year supply.
14/00058 |  | 2015-09-01 | Discovery Park, Ramsgate Road | Sandwich | 633055 | 159544 | Not Started | 500 | 0 | 0 | 50 | 50 | 50 | 150 | 350 | Reserved Matters applications submitted/approved and Phasing information provided by developer. 23/01351 Reserved Matters approved for 112 dwellings in May 2025. 25/00459 Reserved Matters application submitted or 356 dwellings. 25/00460 Reserved Matters application submitted for 32 dwellings.
23/00205 |  | 2024-05-28 | Land at Church Field Farm, The Street | Sholden | 635980 | 152340 | Not Started | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | No Reserved Matters application received and no phasing information submitted. Not included within 5 year supply.
24/00006 |  | 2024-05-20 | Land at New Townsend Farm | St Margaret's At Cliffe | 635710 | 145249 | Not Started | 15 | 0 | 0 | 15 | 0 | 0 | 15 | 0 | Reserved Matters application submitted and awaiting determination (25/00968). Phasing based on developer information.
[7 empty] | Total | 1118 | 0 | 0 | 65 | 101 | 97 | 263 | 855

## A5. Allocations
A5. Phasing site allocations - without consent
Policy Site reference | Site Address | Site Status | Application number | Date Planning App Received | Total Site Allocation units | Total units on application (if received) | Phasing 2025/26 | Phasing 2026/27 | Phasing 2027/28 | Phasing 2028/29 | Phasing 2029/30 | Five year Total | Phasing 2030 onwards | Summary of Phasing evidence (Sept 2025)
SAP1 | Whitfield Urban Expansion - See Worksheet A6. for information. | [12 empty] | See Worksheet A6.
SAP3 | Dover Waterfront (Part DOV017) 1 - 5 Waterloo Crescent, Dover | Allocated / Not Started |  |  | 260 |  | 0 | 0 | 0 | 0 | 0 | 0 | 243 | Discussions undweray with Landowner on planning application / delivery. Phasing in accordance with Appendix DII - Local Plan Housing Site Allocations Trajectory. Expected outside of 5 years. See row below.
|  | Allocated / Application Received | 25/00318 | 2025-03-21 |  | 17 | 0 | 0 | 9 | 8 | 0 | 17 | 0 | Full application received for part of SAP3 in March 2025 (17 units). Awaiting determination. Phasing as advised by landowner.
SAP6 | Dover Mid Town (DOV018) | Allocated / Not Started |  |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100 | Advised by landowner / Developer that phasing remains in accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP7 | Bench Street, Dover (Part DOV017) | Allocated / Not Started |  |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100 | Landowner advise early pre-application assessments have commenced. Phasing in accordance with Appendix DII - Local Plan Housing Site Allocations Trajectory outisde of 5 years.
SAP8 | Land adjacent to Gas Holder, Coombe Valley Road, Dover (DOV022B) | Allocated / Not Started |  |  | 80 |  | 0 | 0 | 0 | 0 | 0 | 0 | 80 | No additional information received. Phased in accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP11 | Westmount College, Folkestone Road, Dover (DOV026) | Allocated / Not Started |  |  | 60 |  | 0 | 0 | 0 | 0 | 0 | 0 | 60 | No additional information received. Phased in accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP12 | Car Park rear of Charlton Shopping Centre, Crafford Street, Dover (DOV028) | Allocated / Not Started |  |  | 100 |  | 0 | 0 | 0 | 0 | 0 | 0 | 100 | Site owner has confirmed no immediate plans for development. Phased in accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory outside of 5 year period.
SAP13 | Land at Dundedin Drive (south), Dover (DOV006) | Allocated / Not Started |  |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 8 | 0 | Landowner estimated timescale for planning application submission within 2 years (by 2027). Pre-application discussions underway. Phasing of site moved into year 5.
SAP13 | Albany Place Car Park, Dover (DOV019) | Allocated / Not Started |  |  | 20 |  | 0 | 0 | 0 | 10 | 10 | 20 | 0 | Landowner estimated timescale for planning application submission by Q4 of 2025/26 (pre-application stage complete). Phasing of site moved into years 4 & 5.
SAP13 | Land north of Coombe Valley Rd, Dover (DOV022C) | Allocated / Not Started |  |  | 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | Part of this site has outline consent: 10 units (21/00935) and is shown on tab A3. Remaining 10 units phased outside of 5 year period as no update received.
SAP13 | Land at Durham Hill, Dover (DOV030) | Allocated / Not Started |  |  | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | No update from landowner. Phased outside of 5 year period.
SAP13 | Land at Roosevelt Road, Dover (TC4S027) | Allocated / Not Started |  |  | 10 |  | 0 | 0 | 0 | 0 | 10 | 10 | 0 | Landowner estimated timescale for planning application submission by 2027/28. Phasing of site delivery moved into year 5.
SAP13 | Land at Peverell Road, Dover (TC4S028) | Allocated / Not Started |  |  | 6 |  | 0 | 0 | 0 | 0 | 6 | 6 | 0 | Landowner estimated timescale for planning application submission by 2027/28. Phasing of site delivery remains in 2029/30 as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP13 | Land at Colton Crescent, Dover (TC4S030) | Allocated / Not Started |  |  | 10 |  | 0 | 0 | 0 | 0 | 9 | 9 | 1 | Landowner estimated timescale for planning application submission by 2027/28. Phasing of site delivery remains in 2029/30 as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP15 | Land at Rays Bottom, Walmer (WAL002) | Allocated / Not Started |  |  | 75 |  | 0 | 0 | 0 | 0 | 25 | 25 | 50 | Developer estimated timescale for planning application submission by end of September 2025. Phasing of site delivery based on submitted phasing information.
SAP16 | Bridleway Riding School, Station Road, Deal (TC4S008) | Allocated / Application Received | 25/00320 | 2025-03-31 | 25 | 30 | 0 | 0 | 15 | 15 | 0 | 30 | 0 | Full Application received in March 2025 (25/00320) for 30 dwellings. Developer estimates delivery within 5 years.
SAP16 | Ethelbert Road garages, Deal (TC4S032) | Allocated / Not Started |  |  | 5 |  | 0 | 0 | 0 | 0 | 5 | 5 | 0 | Landowner estimated timescale for planning application submission by 2027. Phasing of site delivery remains in 2029/30 as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP16 | 104 Northwall Road, Deal (TC4SO47) | Allocated / Planning application received | 24/01322 | 2024-12-19 | 8 | 6 | 0 | 0 | 0 | 6 | 0 | 6 | 0 | Application received in December 2024 (24/01322) for 6 dwellings - awaiting determination. Phasing of site delivery remains in 2028/29 as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory.
SAP16 | Land to the east of Northbourne Road, Great Mongeham (GTM003) | Allocated / Application Received | 25/00736 | 2025-06-25 | 10 | 11 | 0 | 0 | 0 | 0 | 11 | 11 | 0 | Application received in June 2025 (25/00736) for 11 dwellings. Phasing of site delivery remains in 2029/30 as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP17 | Land south of Stonar Lake and to north and east of Stonar Gardens, Sandwich (SAN004) | Allocated / Not Started |  |  | 75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 75 | No additional information received. Phased In accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP18 | Sandwich Highway Depot/Chippies Way, Ash Road, Sandwich (SAN006) | Allocated / Not Started |  |  | 32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 32 | No additional information received. Phased outside of 5 year period.
SAP19 | Land known as Poplar Meadow, Adjacent to 10 Dover Road, Sandwich (SAN007) | Allocated / Not Started |  |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35 | No additional information received. Phased in accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP20 | Woods' Yard, rear of 17 Woodnesborough Road, Sandwich (SAN008) | Allocated / Not Started |  |  | 35 |  | 0 | 0 | 0 | 0 | 0 | 0 | 35 | No additional information received. Phased outside of 5 year period.
SAP21 | Land adjacent to Sandwich Technology School, Deal Road, Sandwich (SAN013) | Allocated / Application Received | 25/00665 | 2025-06-09 | 45 | 45 | 0 | 0 | 0 | 0 | 25 | 25 | 20 | Outline Application received in June 2025 (25/00665) for 45 dwellings and a 60 bed care home. Phasing of first site delivery remains in 2029/30, as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory. Care home phased outside - see below.
[6 empty] | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 60 bed care home is propoosed as part of application. Calcualtion toward housing supply as set out in Housing Delivery Test Rule Book. calculation = # bedrooms / #adults per household 60/1.9=31.57 (rounded down to 31 units) Phased outside of 5 year period as delivery information / provider not known.
SAP22 | Land at Archers Low Farm, St George's Road, Sandwich (SAN023) | Allocated / Application Received | 25/00472 | 2025-04-22 | 18 | 36 | 0 | 0 | 0 | 0 | 18 | 18 | 18 | Outline application for 36 dwellings received in April 2025 and awaiting determination. Part Phasing moved to year 5 based on estimated build out rates.
SAP23 | Sydney Nursery, Dover Road, Sandwich (SAN019) | Allocated / Not Started |  |  | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | No additional information received. Phased outside of 5 year period.
SAP24 | Land to the of South Aylesham (AYL003) | Allocated / Application Received | 25/00133 | 2025-02-01 | 640 | 800 | 0 | 0 | 0 | 20 | 50 | 70 | 730 | Outline Application submitted in February 2025 for up to 800 homes (25/00133) and currently under consideration. Phasing largely updated to reflect landowner/developer information received in September 2025, with some amendments to push back estimated first completions to 2028.
SAP27 | Land at Dorman Avenue North, Aylesham (AYL001) | Allocated / Not Started |  |  | 9 |  | 0 | 0 | 0 | 0 | 10 | 10 | 0 | Landowner estimated timescale for planning application submission by 2027 indicating 10 units. Delivery of site expected in year 5.
SAP28 | Land between Eythorne and Elvington (EYT003/EYT09/EYT012) | Allocated / Not Started |  |  | 300 |  | 0 | 0 | 0 | 0 | 0 | 0 | 300 | Landowner estimated timescale for planning application submission in less than 5 years. Phasing of site delivery remains after 2030, as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory.
SAP29 | Land on the south eastern side of Roman Way, Elvington (EYT008) | Allocated / Not Started |  |  | 50 |  | 0 | 0 | 0 | 0 | 0 | 0 | 50 | Developer estimates applicaton submission in 2026/27 and completions in 2028/29. However, phased outside of 5 years at this time.
SAP30 | Land at Chapel Hill, Eythorne (TC4S039) | Allocated / Not Started |  |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Landowner estimated timescale for planning application submission by 2029. Phasing of site delivery remains after 2030, as set out in Appendix Dii - Local Plan Housing Site Allocations Trajectory.
SAP32 | Land at Buttsole Pond, Lower Street, Eastry (EAS002) | Allocated / Planning application received | Outline 25/00934 | 2025-08-15 | 80 | 100 | 0 | 0 | 0 | 0 | 25 | 25 | 75 | Outline application for 100 dwellings received in August 2025 (25/00934). Developer information states full delivery within 5 year period at 50 per annum from 2027/28. However. some site phasing moved out of 5 year period as application not yet determined and is outline, not full.
SAP33 | Eastry Court Farm, Eastry (EAS009) | Allocated / Planning application Granted | 24/00866 | Granted 17/06/2025 | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 5 | 0 | Application granted June 2025 for 5 units. Phasing moved into year 3.
SAP33 | Land adjacent to Cross Farm, Eastry (EAS009) | Allocated / Planning application received | 25/00005 | 2025-02-03 | 10 | 9 | 0 | 0 | 0 | 9 | 0 | 9 | 0 | Full Application received in February 2025 for 9 units. Phasing moved into year 4 based on estimated build out rates for site size.
SAP34 | Land at Woodhill Farm, Ringwould Road, Kingsdown (KIN002) | Allocated / Planning application received | 25/00112 | 2025-02-04 | 50 | 70 | 0 | 0 | 0 | 30 | 40 | 70 | 0 | Full Planning application received in Feb 2025 for 70 units following pre-application engagement. Application awaiting determination. Phased in years 4/5.
SAP35 | Land adjacent to Courtlands, Kingsdown (TC4S074) | Allocated / Not Started |  |  | 5 |  | 0 | 0 | 0 | 0 | 5 | 5 | 0 | No additional information received. Part Phasing moved to year 5 due to site size and build out rates.
SAP36 | Land north and east of St Andrew's Gardens and adjacent to Mill House, Sheperdswell (SHE004/ TC4S082) | Allocated / Planning application granted / received | RM 25/00908 Outline 22/01207 | 2025-08-06 | 50 | 48 | 0 | 0 | 9 | 9 | 18 | 36 | 12 | 2 land parcels. Outline consent (22/01207) granted in June 2025 for 39 units and subsequent Reserved Matters submitted (25/00908) - awaiting decision. Full application received in Feb 2023 (23/00235) for 9 units, awaiting decision. Phasing based on estimated build out rates.
SAP37 | Land at Botolph Street Farm, Shepherdswell (SHE006) | Allocated / pre-app received |  |  | 10 |  | 0 | 0 | 0 | 0 | 10 | 10 | 0 | Pre-application advice provided in 2024. Site phased in year 5.
SAP37 | Land off Mill Lane, Shepherdswell (SHE008) | Allocated / Not Started |  |  | 10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | No additional information received. Phased in accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP38 | Land adjacent to Reach Road bordering Reach Court Farm, St Margarets (STM003) | Allocated / Not Started |  |  | 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | No additional information received. Phased in accordance with Appendix Dii - Local Plan Housing Site Allocations Trajectory
SAP39 | Land to the west of Townsend Farm Road, St Margarets (STM007/STM008) | Allocated / Not Started |  |  | 36 |  | 0 | 0 | 0 | 0 | 0 | 0 | 36 | No additional information received. Phased outside of 5 year period.
SAP42 | Land adjacent to Staple Road, Wingham (WIN003) | Allocated / Not Started |  |  | 20 |  | 0 | 0 | 0 | 0 | 10 | 10 | 9 | Developer has advised they are intending to submit full application for 19 units in October 2025. Phased in part in year 5 in accordance with developer information .
SAP42 | Land adjacent to White Lodge, Preston Hill, Wingham (WIN004) | Allocated / Not Started |  |  | 8 |  | 0 | 0 | 0 | 4 | 4 | 8 | 0 | Developer intending to submit application in September 2025 based on information recieved. Phased in accordance with developer information. There are currently no underlying issues which affect the delivery of the site.
SAP45 | Land known as the former Archway Filling Station, New Dover Road, Capel-le-Ferne (CAP011) | Allocated / Not Started |  |  | 10 |  | 0 | 0 | 0 | 5 | 5 | 10 | 0 | No additional information received in 2025 survey. Phased into years 4/5 due to site size and estimated build out rates.
SAP46 | Land adjacent Langdon Court Bungalow, The Street, East Langdon (LAN003) | Allocated / Planning application received | Outline 23/00370 | 2023-03-09 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | Application - outline for 40 units (23/00370) resolution to grant in Jan 2024, subject to finalisation of legal agreement. Remains out of 5 years until consent granted as no response received in relation to S106 progress.
SAP47 | Land adjacent to Lydden Court Farm, Church Lane, Lydden (LYD003) | Allocated / Planning application received | Outline 23/01061 | 2023-08-24 | 30 | 23 | 0 | 0 | 0 | 10 | 13 | 23 | 0 | Outline application for 23 dwellings received in August 2023 (23/01061) has resolution to grant at Planning committee, subject to finalisation of legal agreement. Phasing moved to years 4/5 based on information in relation to S106 progress.
SAP48 | PRE016 - Site north of Discovery Drive, Preston | Allocated / Not Started |  |  | 65 |  | 0 | 0 | 0 | 0 | 7 | 7 | 10 | Site allocation in 3 land ownership parcels. This DDC owned parcel is being considered for 17 dwellings. Landower have advised on intention to submit planning application prior to end of 2027 and pre-application discussions ongoing. Part phased in year 5.
SAP48 | PRE003 - Apple Tree Farm, Stourmouth Road | Allocated / Planning application received | 25/00105 | 2025-01-31 |  | 8 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | Site allocation in 3 land ownership parcels. Full Application received in 2025 for part of this site and awaiting determination (25/00105). Estimated delivery within year 5.
SAP48 | Apple Tree Farm and west of Apple Tree Farm, Preston (PRE003/PRE016/ PRE017) (PRE017 - this app for Land north east of Grove Road, Preston) | Allocated / Planning application received | Outline 24/01331 | 2024-12-23 |  | 53 | 0 | 0 | 0 | 0 | 9 | 9 | 44 | Site allocation in 3 land ownership parcels. An outline application for 53 dwellings was received in December 2024 for this part of the allocated site - under consideration. Some units estimated in year 5.
SAP49 | Land to the east of Jubilee Road, Worth (WOR006) | Allocated / Not Started |  |  | 10 |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 | No additional information received. Part Phasing moved to year 5 due to site size and build out rates.
SAP49 | Land to the East of former Bisley Nursery, The Street, Worth (WOR009) | Allocated / Not Started |  |  | 15 |  | 0 | 0 | 0 | 0 | 9 | 9 | 6 | No additional information received. Part Phasing moved to year 5 due to site size and build out rates.
SAP50 | Land Adjacent to Short Street, Chillenden (GOO006) | Allocated / Not Started |  |  | 5 |  | 0 | 0 | 0 | 0 | 5 | 5 | 0 | No additional information received. Phasing moved to year 5 due to site size and build out rates.
SAP51 | Land Opposite the Conifers, Coldred (SHE013) | Allocated / Planning application received | Outline 21/00882 | 2021-05-28 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | Outline Appliction received in May 2021 (21/00882) The application received a resolution to grant outline planning permission at committee and is awaiting section 106 legal agreement to be completed - phased in year 5 based on information about S106 progress.
SAP53 | Land at Ringwould - Alpines, Dover Road (RINOO2/RIN006) | Allocated / Planning application received | 24/00165 | 2024-02-12 | 10 | 9 | 0 | 0 | 0 | 0 | 9 | 9 | 0 | Outline 24/00165 received in February 2024 for 9 dwellings and given resolution to grant at Planning Committee in July 2025.
SAP54 | Land at Durlock Road, Staple (STA004) | Allocated / Not started |  |  | 3 |  | 0 | 0 | 0 | 0 | 3 | 3 | 0 | Application was withdrawn for 6 dwellings. No additional information received. Phasing moved to year 5 due to site size and build out rates.
SAP55 | Land south of Sandwich Road, Woodnesborough (WOO006) | Allocated / Not Started |  |  | 8 |  | 0 | 0 | 0 | 0 | 8 | 8 | 0 | No additional information received. Phasing moved to year 5 due to site size and build out rates.
ANP7a | Agri/Cowans Land, Land south of Sandwich Road, Ash (ASH014) | Allocated / Planning application received | 20/00284 |  | 45 | 37 | 0 | 0 | 5 | 9 | 8 | 22 | 15 | Part of site has outline consent (see outline applications) and further hybrid application recieved for 37 units (22 with full consent) (20/00284) recommendation to approve consent, subject to agreement of planning obligations.
ANP7b | Old Council Yard, Land to the west of Chequer Lane, Ash (ASH015) | Allocated / Not Started | PE/20/00196 |  | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | No update from landowner. Phased outside of 5 year period.
ANP7d | Land North of Molland Lane, Ash (ASH004) | Allocated / Not Started |  |  | 105 |  | 0 | 0 | 0 | 0 | 0 | 0 | 105 | No update from landowner. Phased outside of 5 year period.
ANP7e | Land south of Guilton (ASH011) | Allocated / Not Started |  |  | 9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 9 | Land owners agent responded. Phased outside of 5 year period, 2030/2031.
[6 empty] | Total | 0 | 0 | 43 | 143 | 385 | 571 | 2516

## A6. Whitfield UE
A6. Phasing extant Whitfield Urban Expansion reserved matters applications pursuant to outline 10/01010
Application number/s | Phase / Developer | Extant Units 2024/25 | Phasing 2025/26 | Phasing 2026/27 | Phasing 2027/28 | Phasing 2028/29 | Phasing 2029/30 | Five year Total | Phasing 2030/31 | Phasing 2031/32 | Phasing 2032/33 | Phasing 2033/34 | Phasing 2034/35 | 10 year total | Beyond 2035 | Phasing Summary 2025
10/01010 | Phase 1 - Outline Consent remaining units without RM approved. Outline granted for 1,250 units. 327 remain without RM approval. | 327 | 0 | 0 | 10 | 50 | 50 | 110 | 50 | 50 | 50 | 50 | 17 | 327 | 0 | Reserved Matters planning applications for the remainder of Phase 1 outline have been submitted in early 2025 (25/00486; 25/00487; 25/00488; 25/00172). Please note, some of these applications are for the same parcels of land, and all are awaiting determination. The previous restriction of 800 homes being occupied until Whitfield roundabout upgrades has been removed. Based on previous built out rates, multiple housebuilders on-site and reciept of Reserved Matters applications, phasing for 110 units is now within 5 year period. Remaining 217 is phased outside of 5 year period
18/01238 22/01608 22/00029 22/00219 20/00640 20/00718 & S73 22/01166 | Phase 1 - with RM Consent approved Extant units (note 471 completions as of 31st March 2025 on Phase 1 RMs) | 452 | 72 | 85 | 72 | 72 | 72 | 373 | 72 | 7 | 0 | 0 | 0 | 452 | 0 | Reserved Matters applications - under construction. Phasing is based on previous years built out rates and information from multiple housebuilders on-site as of September 2025.
DOV/23/00830 | Phase 2 - (Pentland) | 300 | 0 | 0 | 0 | 0 | 25 | 25 | 24 | 24 | 25 | 36 | 36 | 170 | 130 | Outline application received resolution to grant at Planning Committee in April 2025. Phasing based on information from developer as of September 2025.
DOV/23/01458 | Phase 2 - (Danescroft) | 445 | 0 | 0 | 0 | 0 | 17 | 17 | 47 | 48 | 40 | 18 | 18 | 188 | 257 | Hybrid application (445 dwellings with 88 in full) received resolution to grant at Planning Committee in April 2025. Phasing based on information from developer as of September 2025.
N/A | Remaining SAP1 Allocation (SAP1 total is 6,350 homes) |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Persimmon Homes (lead housebuilder) have commenced masterplanning required by Policy SAP1. Phasing unknown at this time but will be outside of 5 year period.
|  | Total | 72 | 85 | 82 | 122 | 164 | 525 | 193 | 129 | 115 | 104 | 71 | 1137 | 387
[8 empty] | 996 | 1189 | 1318 | 1433 | 1537 | 1608